## Sheet1
extended shift report
Date | Follow up needed Y/N | requested by: | Work Order # | Contacted by: | Location: | Problem: | responded by: | comments: | Contact/customer you communicated resolution to | Open or Closed
2022-07-19 | n | resident | 23W001277 | famis | GM-F402 | fridge light out | M9-M10 | replaced appliance light | resident | close
| n | resident | 23W001346 | famis | BB-K201 | fridge is not working | M9-M10 | inspected refrigerator was cold and working unit appeared to be vacant | VACANT | close
| n | resident | 23W001385 | famis | GM-F406 | bedroom B light out | M9-M10 | replaced bedroom light | resident | close
| n | staff | 23W001391 | famis | GM-F112 LA | leak in laundry room | M9-M10 | washer overflowed | staff | close
| n | resident | 23W001276 | famis | GM-L403 | sink draining slow | M9-M10 | unclogged drainline | resident | close
| n | resident | 23W001133 | famis | OB-087 | pole light out | M9-M10 | replaced light | resident | close
| n | resident | 23W001297 | famis | OB-032 | gurgling sound coming from the sink drain | M9-M10 | checked drainline for the bathroom sink all clear | resident | close
| n | resident | 23W001297 | famis | OB-032 | cabinet door fell | M9-M10 | repaired and reinstalled cabinet door | resident | close
| n | resident | 23W001298 | famis | PL-D-54 | no hot water | M9-M10 | relit water heater | resident | close
| n | resident | 23W000935 | famis | GM-I310 | bedroom light out | M9-M10 | replaced maint light bed C | resident | close
| n | resident | 23W000936 | famis | GM-I310 | sink draining slow | M9-M10 | unclogged drainline | resident | close
| Y | resident | 23W001392 | famis | OB-101 | leak in the restroom next to the kitchen | M9-M10 | cut hole in the drywall,wall was wet and damaged-found pinhole leak in the water line for the toilet clamped to stop leak, will need line repair and wall remediation And repair | follow-up | open
| n | M1 | n/a | radio | PHA-102 | lock up | M9-M10 | secured conference room | staff | close
| n | M1 | n/a | radio | FK- | lock up | M9-M10 | secured 11A,11G,11H,13E,13H | staff | close
| n | M1 | n/a | radio | OB- | lock up | M9-M10 | secured 15,42,55,62,67,94,108 | staff | close